## Metrics
|  | Iteration Status |  |  |  | Automation Coverage %
|  | Completed | In progress
|  | 3/28/2014 | Target date 4/25/14
|  | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Web Components | Total Manual Test Cases | Automated test cases | Automated test cases | Automated test cases | Automated test cases | Current | After iteration 2
Feature page | 15 | 2 | 2 |  |  | 13.33% | 26.67%
Movies page | 60 | 38 | 0 |  |  | 63.33% | 63.33%
My-Collection page | 25 | 1 | 9 |  |  | 4% | 40%
Discovery page | 12 | 2 | 3 |  |  | 16.67% | 41.67%
Rewards page | 30 | 1 | 3 |  |  | 3.333% | 13.33%
Site Navigation | 19 | 0 | 0 |  |  | 0% | 0%
Search page | 3 | 0 | 0 |  |  | 0% | 0%
Movie Details page | 117 | 0 | 3 |  |  | 0% | 2.564%
Disney ID | 4 | 1 | 0 |  |  | 25% | 25%
Account linking | 4 | 0 | 0 |  |  | 0% | 0%
Account setting | 45 | 0 | 0 |  |  | 0% | 0%
Sharing | 10 | 0 | 0 |  |  | 0% | 0%
Iteration 2 Status |  |  |  | 2014-04-28
Web Components | Planed | Completed | Status
Feature page | 2 | 2 | 100%
My-Collection page | 9 | 9 | 100%
Discovery page | 3 | 3 | 100%
Rewards page | 3 | 3 | 100%
Movie Details page | 3 | 3 | 100%
Overall Iteration status | 20 | 20 | 100%

## Feature page
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US2129 - 1 | Featured - Billboard Given I'm authenticated And a preview call to action is displayed And a "details" call to action is displayed (only preview is displayed on the smallest screens) -As of 2/13, details button is displayed as "Buy" And the Billboard image is displayed And there is a title displayed on the billboard When I select the Billboard Then the Movie Details Page related to the Billboard is displayed | Scenario: An authenticated guest previews a billboard Given an authenticated guest has navigated to the featured page And a movie details billboard exists When an authenticated guest chooses to view movie details Then the movie details page shall be displayed | 1 | Done | Regression
US8962 | Billboards Remove limit of 5 billboards for web Given I'm not logged in When I'm on Featured page Then I should see billboards with no max limitations | Scenario: Display billboards for unauthenticated guest Given an unauthenticated guest enters the DMA site Then billboards shall display not less than 3 banners | 1 | Done | Regression
US2129 -2 | Given I'm unauthenticated And a preview call to action is displayed And a "details" call to action is displayed (only preview is displayed on the smallest screens) And the Billboard image is displayed And there is a title displayed on the billboard When I select the Billboard Then the Movie Details Page related to the Billboard is displayed | Scenario: An unauthenticated guest previews a billboard Given an unauthenticated guest has navigated to the featured page And a movie details billboard exists When an authenticated guest chooses to view movie details Then the movie details page shall be displayed | 2 | Done | Regression
US2132 | Catalog Promotion Billboard - Select Call the Action: "Details" or "More Info" Given I am a Guest And a details call to action is displayed When I select the details button Then the Movie Details Page related to the Billboard is displayed | Scenario: An unauthenticated guest lands on Sign In billboard Given an unauthenticated guest has navigated to the featured page Then billboards shall display not less than 3 banners Then Sign In billboard should be the first billboard | 2 | Done | Regression

## My-Collection
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US1822-1 | View My Collection Landing Page Given I have an existing user ID with entitlements When I select My Collection Then the My Collection Page with the following elements: * Movies Page Header * Favorites Page Header * A list of movies owned by the user ID | Scenario: An authenticated guest views their collection Given an authenticated guest has navigated to the my collection page And the guest has entitlements Then the my collection page shall be displayed with a list of owned movies | 1 | Done | Regression
US1822-2 | Movies Selection Heade When I navigate to the My collection Page Then the Movies header selection is selected | Scenario: An authenticated guest views my-collection page Given an authenticated guest has navigated to the my collection page Then the Movies header selection is selected | 2 | Done | Regression
US2056-1 | Post purchase - My collection Navigation When I'm on the My Collection Page Then I see the My collection Navigation And the My Collection Selection is selected (remains selected until another title is selected) And the Movies Selection is selected | Scenario: An authenticated guest views my-collection page Given an authenticated guest has navigated to the my collection page Then my collection page navigation displayed Then the Movies header selection is selected | 2 | Done | Regression
US2056-2 | Select Movie in My Collection and see the Movie Details Given there is a movie belonging to the userid And there are more than zero titles displayed When the user selects a movie in my collection Then the Movie details page is displayed | Scenario: An authenticated guest selects a movie and see the movie details Given an authenticated guest has navigated to the my collection page Then the my collection page shall be displayed with a list of owned movies Then guest selects each movie title and views movie details | 2 | Done | Regression
US2056-3 | Sorting When I select to sort my collection Then the sort options are displayed * Sort by release date - ascending, descending * Sort by name - alphabetical - ascending, descending * Most Recent - purchase date - ascending, descending (default) * Secondary sort by name, ascending | Scenario: An authenticated guest presented with movies collection sort options Given an authenticated guest has navigated to the my collection page And my collection page sort button is available Then available sort options displayed | 2 | Done | Regression
US2570 - 1 | Given I'm logged in When I Click the MOVIES tab in My Collection Then the the Movies in My Collection with the "My Collection" ribbon appears | Scenario: An authenticated guest views my-collection page and "My Collection" ribbon appears Given an authenticated guest has navigated to the my collection page Then movies owned by the guest should appear with "My Collection" ribbon | 2 | Done | Regression
US2570 - 2 | Given I am a logged in guest When I Click the FAVORITES tab in My Collection Then the Favorited movies with the "Favorited" ribbons appear | Scenario: An authenticated guest views my-collection page and "Favorites" ribbon appears Given an authenticated guest has navigated to the my collection page When favorites is selected Then a list of movies shall appear with "Favorites" ribbon | 2 | Done | Regression
US2943 - 1 | Default Sorting for Movies and Favorites Given I'm logged in When I access my collection Then the default sorting for movies and favorites is by Date Added to my collection (This could be via a transaction, a like action, linking or a code redemption.) | Scenario: An authenticated guest views my-collection page and movies sorted with "Date Added" option Given an authenticated guest has navigated to the my collection page Then default sort option should be Date Added | 2 | Done | Regression
US2943 - 2 | Ability to Favorite Movies and Videos Given I'm logged in When I want to select an item as a favorite Then I can favorite Movies And I can favorite videos | Scenario: An authenticated guest can favorite owned movies Given an authenticated guest has navigated to the my collection page Then the my collection page shall be displayed with a list of owned movies When guest selects one of the movie Then movie details page displayed with favorite option Then guest adds selected movie to favorites Then selected movie appears under Favorites section on My-Collection page | 2 | Done | Regression
US2943 -3 | Favorite Movies and Videos appearing on tabs Given I'm logged in When I have favorited Movies and Videos Then those movies and videos are displayed in different (Movies and Videos) tabs inside of the favorites tab | Scenario: An authenticated guest views list of favorited videos Given an authenticated guest has navigated to the my collection page And selects a favorites header Then Movies and Videos sub headers are showing Then guest selects a Videos header Then all favorites videos with "Favorites" ribbon are displayed | 2 | Done | Regression

## Discover
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US1795 | Discover - Landing Page Given I am not logged in When I'm on Discover page Then I see the thumbnails, title and runtime | Scenario: An unauthenticated guest navigates to the Discover page Given an unauthenticated guest has navigated to the discover page Then the Discover page shall be displayed with video's thumbnails, titles and run times | 1 | Done | Regression
US2557 | Discover - Video Modal Metadata Given I am logged in And I'm on Discover page When I click on a thumbnail of a category Then I see the thumbnails, title and runtime | Scenario: An unauthenticated guest navigates to the Discover page Given an authenticated guest has navigated to the discover page Then the Discover page shall be displayed with video's thumbnails, titles and run times | 1 | Done | Regression
US1795 - 3 | Discover - Landing Page Given I am not logged in And I'm on Discover page When I click on a thumbnail Then I see a detail Discover video page with description and play button Then I see the thumbnails, title and runtime I can click on one of thumbnails Then I see video details including thumbnail of the video, title, description (when it is applicable), runtime, favorite button, and share button I can click on play button Then I see a login page (Log in is required to watch a video) | Scenario: An authenticated guest navigates to the Discover page and selects video Given an authenticated guest has navigated to the discover page Then the discover page shall be displayed Then guest selects random video Then popup window will be displayed video thumbnail with expected options | 2 | In Progress | Regression
US1813 | Discover - Favorite Button - 1 - AC 4.0 - Authenticate to favorite content Given, I'm not authenticated on the site Given, I'm not logged in to the site Then I see the thumbnails, title and video duration I can click on one of thumbnails I can select the favorite icon/button Then the system launches the authentication flow overlay (separate story) After I complete authentication successfully, the modal closes Then I see a login page (Log in is required to favorite a video) and logged in to the site The video detail page displays and the favorite icon is selected and turned red And the favorited title is added under My Collection - Favorite tab (add a story for My Collection) | Scenario: An unauthenticated guest adds video to favorites Given an unauthenticated guest has navigated to the discover page Then guest selects random video And guest trying to add video to favorites Then guest presented with login lightbox and signs in Then guest selects the video which he wants to add to favorites And guest adds video to favorites Then popup window will be displayed video thumbnail with expected options Then video appears under Favorites Videos section on MyCollection page | 2 | done | Regression
US1813 -2 | Discover - Favorite Button - 2 - AC 1.0 - Favorite Path Unsuccessful Given, I'm not authenticated on the site Given, I'm not logged in to the site Then I see the thumbnails, title and video duration I can click on one of thumbnails When I select the favorite icon/button Then the system launches the authentication flow overlay (separate story) If authentication is unsuccessful Then I see a login page (Log in is required to favorite a video) I can x out from the login page Then I can go back to Video details The system displays the favorite icon/button as unselected | Scenario: An unauthenticated guest trying to add video to favorites Given an unauthenticated guest has navigated to the discover page Then guest selects random video And guest trying to add video to favorites Then guest presented with login and closes it Then video still not favorites | 2 | done | Regression

## Rewards
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US2693 - 1 | Rewards - Points Counter Given I'm logged in When I have no DMR points and I'm viewing the Rewards page Then the points counter is listed as 00000 | Scenario: An unauthenticated guest views Disney Movie Rewards Given an unauthenticated guest has navigated to the rewards page Then the rewards page shall be displayed And the unauthenticated guest shall have 00000 movie reward points | 1 | Done | Regression
US2693 -2 | Points Counter Given I'm logged in When I have DMR points and I'm viewing the Rewards page Then the DMR points are displayed | Scenario: An authenticated guest views Disney Movie Rewards Given an authenticated guest has navigated to the rewards page Then the rewards page shall be displayed Then the authenticated guest shall have movie reward points | 2 | Done | Regression
US2694 | Rewards - Enter Code/Login Given I'm not logged in And I'm on reward page When I click into the code entry form Then the system displays the login page | Scenario: An unauthenticated guest views DMR page and applies a code Given an unauthenticated guest has navigated to the rewards page Then the rewards page shall be displayed And guest entered a code: 'abcd' to redeem Then guest presented with login lightbox and signs in | 2 | Done | Regression
US2698 - 1 | Rewards - SSO to DMR - Single Sign-on Given I'm logged in (and connected accounts with iTunes account - Cindy: As of 2/13 this story is not valid when the account is not linked) When I am on the Rewards page And t I click on the "Get Rewards" button Then the system takes me to http://www.disneymovierewards.go.com/member/index.htm (For QA environment: http://dmr2.spika.com/) | Scenario: An authenticated guest views Disney Movie Rewards and signs in to DMR page Given an authenticated guest has navigated to the rewards page And guest chooses to Get Rewards Then guest redirected and auto signs in to DMR page | 2 | Done | Regression

## Movie Details
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US1609 - 1 | Favorites Button User selects Favorite button Favorite Button appears selected Then the system adds that movie to the favorites section of their My Collection page | Scenario: An authenticated guest adding movie to favorites Given an authenticated guest has navigated to the featured page And movies slider is displayed When guest selects a movie Then movie details page displayed with favorite option Then guest adds selected movie to favorites Then selected movie appears under Favorites section on My-Collection page | 2 | Done | Regression
US1609 - 2 | Favorites Button Given that the Favorite button is selected Then the user deselects Favorite button Then the system removes that item from the favorites section of their My Collection page | Scenario: An authenticated guest remove movie from favorites Given an authenticated guest has navigated to the my collection page When favorites is selected Then a list of movies shall appear with "Favorites" ribbon Then guest selects favorited movie Then movie details page displayed with favorite option And guest removes movie from favorites Then selected movie is not appears under Favorites section on My-Collection page | 2 | Done | Regression
US1609 - 3 | Favorites Button Given that the user is not authenticated Then the user selects the Favorite button Then the system presents the login lightbox Then the favorite button appears selected Then the system adds that movie to the favorites section of their My Collection page | Scenario: An unauthenticated guest trying to add movie to favorites Given an unauthenticated guest enters the DMA site And movies slider is displayed When guest selects a movie Then movie details page displayed with favorite option And guest trying to add selected movie to favorites Then guest presented with login lightbox and logged in Then guest adds selected movie to favorites Then selected movie appears under Favorites section on My-Collection page | 2 | Done | Regression

## Movies
User Storry ID | Manual Test Case | Cucumber Story | Iteration | Status | Test cycle
US1765 1 - 19 | Movies - Menu Given, I'm not authenticated on the site And, I select "All Movies" in the Browse section Then, the "All Movies" collection appears { Same Given step 2. And I select "Marvel's Cinematic Universe" in the Browse section Then the "Marvel's Cinematic Universe" collection appears 3. And, I select "Action & Adventure" in the Browse section Then, the "Action & Adventure" collection appears 4. And, I select "Disney•Pixar" in the Browse section Then, the "Disney•Pixar" collection appears 5. And, I select "Animation" in the Browse section Then, the "Animation" collection appears 6. And, I select "Disney Princesses" in the Browse section Then, the "Disney Princesses" collection appears 7. And, I select "Song & Dance" in the Browse section Then, the "Song & Dance" collection appears 8. And, I select "Classics" in the Browse section Then, the "Classics" collection appears 9. And, I select "Classics" in the Browse section Then, the "Classics" collection appears 10. And, I select "Disney Fairies" in the Browse section Then, the "Disney Fairies" collection appears 11. And, I select "Sports" in the Browse section Then, the "Sports" collection appears 12. And, I select "A Little Romance" in the Browse section Then, the "A Little Romance" collection appears 13. And, I select "Muppet Mayhem" in the Browse section Then, the "Muppet Mayhem" collection appears 14. And, I select "Inspired by a True Story" in the Browse section Then, the "Inspired by a True Story" collection appears 15. And, I select "Disney Dogs" in the Browse section Then, the "Disney Dogs" collection appears 16. And, I select "Mickey & Friends" in the Browse section Then, the "Mickey & Friends" collection appears 17. And, I select "Winnie the Pooh" in the Browse section Then, the "Winnie the Pooh" collection appears 18. And, I select "Heroes" in the Browse section Then, the "Heroes" collection appears 19. And, I select "Documentaries" in the Browse section Then, the "Documentaries" collection appears } | Scenario: An unauthenticated guest browses a category Given an unauthenticated guest has navigated to the movies page When a guest browses each movies categories Then the selected category page shall be displayed | 1 | Done | Regression
US1765 1-19 | Movies - Menu Given, I'm authenticated on the site And, I select "All Movies" in the Browse section Then, the "All Movies" collection appears { Same Given step 2. And I select "Marvel's Cinematic Universe" in the Browse section Then the "Marvel's Cinematic Universe" collection appears 3. And, I select "Action & Adventure" in the Browse section Then, the "Action & Adventure" collection appears 4. And, I select "Disney•Pixar" in the Browse section Then, the "Disney•Pixar" collection appears 5. And, I select "Animation" in the Browse section Then, the "Animation" collection appears 6. And, I select "Disney Princesses" in the Browse section Then, the "Disney Princesses" collection appears 7. And, I select "Song & Dance" in the Browse section Then, the "Song & Dance" collection appears 8. And, I select "Classics" in the Browse section Then, the "Classics" collection appears 9. And, I select "Classics" in the Browse section Then, the "Classics" collection appears 10. And, I select "Disney Fairies" in the Browse section Then, the "Disney Fairies" collection appears 11. And, I select "Sports" in the Browse section Then, the "Sports" collection appears 12. And, I select "A Little Romance" in the Browse section Then, the "A Little Romance" collection appears 13. And, I select "Muppet Mayhem" in the Browse section Then, the "Muppet Mayhem" collection appears 14. And, I select "Inspired by a True Story" in the Browse section Then, the "Inspired by a True Story" collection appears 15. And, I select "Disney Dogs" in the Browse section Then, the "Disney Dogs" collection appears 16. And, I select "Mickey & Friends" in the Browse section Then, the "Mickey & Friends" collection appears 17. And, I select "Winnie the Pooh" in the Browse section Then, the "Winnie the Pooh" collection appears 18. And, I select "Heroes" in the Browse section Then, the "Heroes" collection appears 19. And, I select "Documentaries" in the Browse section Then, the "Documentaries" collection appears } | Scenario: An authenticated guest browses a category Given an authenticated guest has navigated to the movies page When a guest browses each movies categories Then the selected category page shall be displayed | 1 | Done | Regression